## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 18 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Activity 21 | 0 | 0 | 0 | 0 | 0%
code to make theme selector work | 21 | 2 | 0 | 0 | 0%
make page themes | 20 | 1 | 18 | 0 | 0%
Automcatically detect input language | 25 | 5 | 0 | 0 | 0%
Secure API key in backend proxy server? | 26 | 7 | 0 | 0 | 0%
Create UI plan | 1 | 1 | 1 | 1 | 100%
Design UI layout | 1 | 4 | 1 | 17 | 100%
Make text boxes | 1 | 2 | 1 | 2 | 100%
Research API | 1 | 7 | 1 | 18 | 100%
Create buttons for languages | 2 | 2 | 2 | 1 | 100%
Create morse code library | 3 | 3 | 3 | 1 | 100%
Create text input box | 4 | 3 | 3 | 1 | 100%
Create text output box | 4 | 3 | 3 | 1 | 100%
If text too big for box, can scroll down inside box | 4 | 2 | 3 | 1 | 100%
Make JS code to translate morse code | 5 | 5 | 3 | 4 | 100%
Create system to translate letters to morse | 3 | 3 | 4 | 2 | 100%
Use dropdown to select input | 4 | 4 | 4 | 1 | 100%
Use dropdown to select output | 4 | 4 | 5 | 2 | 100%
Create buttons for copy, text to speech, about etc | 7 | 2 | 10 | 1 | 100%
Create dropdown for theme | 21 | 2 | 10 | 1 | 100%
Link github page | 11 | 1 | 11 | 1 | 100%
mid-project review | 15 | 3 | 15 | 3 | 100%
Make code to reverse dropdown values | 11 | 2 | 16 | 1 | 100%
Link an about page with button | 12 | 2 | 16 | 1 | 100%
Make translation occur upon input - no button | 22 | 2 | 16 | 1 | 100%
integrate api translator | 7 | 7 | 17 | 2 | 100%